## All
Critical | Task Description | Duration | Start Date | End Date
| Research Components | 6 hrs | 2021-01-15 | 2021-01-16
• | Design System | 6 hrs | 2021-01-18 | 2021-01-20
| Design Display UI | 4 hrs | 2021-04-02 | 2021-04-03
| Design Wind Sensing Unit | 9 hrs | 2021-03-07 | 2021-03-12 | Completed
| Assemble Wind Sensing Unit | 13 hrs | 2021-04-12 | 2021-04-19 | In Progress
| Design Mobile Application | 12 hrs | 2021-02-10 | 2021-02-17 | Not Started
| Test Bluetooth Communication | 12 hrs | 2021-04-13 | 2021-04-19
| Research Bluetooth | 6 hrs | 2021-02-19 | 2021-02-20
| Code Microcontrollers | 114 hrs | 2021-01-29 | 2021-04-05
| Test Components | 12 hrs | 2021-01-25 | 2021-01-30
| Mount Hardware | 12 hrs | 2021-03-14 | 2021-03-20
| Test Accuracy of Calculations | 14 hrs | 2021-04-12 | 2021-04-19
| Weatherproof | 3 hrs | 2021-04-14 | 2021-04-14
| Test Durability | 6 hrs | 2021-04-16 | 2021-04-17
| Research Data Collection | 8 hrs | 2021-03-17 | 2021-03-20
| Research Data Analysis | 6 hrs | 2021-03-17 | 2021-03-19
• | Research Mobile Development | 10 hrs | 2021-01-13 | 2021-01-20
• | Code Mobile Application | 78 hrs | 2021-02-19 | 2021-04-03
• | Debugging | 27 hrs | 2021-04-05 | 2021-04-19